## Sheet1
Task ID | Task Name | Start Date | End Date | Duration | Depends on
1.1 | Define project charter and scope |  |  | Week 1-2
1.2 | Create WBS and Gantt chart |  |  | Week 1-2
1.3 | Weekly progress review and adjustments |  |  | Week 1-2
1.4 | Final report and presentation |  |  | Week 1-2
2.1 | Set up development environment |  |  | Week 1-2
2.2 | Integrate FastF1 and configure data caching |  |  | Week 1-2
2.3 | Define data schema for laps, stints, and tyres |  |  | Week 1-2
2.4 | Implement data validation and basic sanity checks |  |  | Week 1-2
3.1 | Implement lap time and sector analysis |  |  | Week 3-4
3.2 | Implement stint segmentation |  |  | Week 3-4
3.3 | Develop initial tyre degradation model |  |  | Week 3-4
3.4 | Implement simple strategy scenario |  |  | Week 3-4
4.1 | Design dashboard layout and user flows |  |  | Week 5
4.2 | Implement basic Streamlit app structure |  |  | Week 5
4.3 | Add lap and stint visualization components |  |  | Week 5
4.4 | Add strategy comparison interface and results view |  |  | Week 5
5.1 | Write unit tests for core data processing functions |  |  | Week 6
5.3 | Conduct integration tests for end-to-end race analysis |  |  | Week 6
5.4 | Validate model outputs against known race results |  |  | Week 6
6.1 | Prepare requirements.txt and configuration files |  |  | Week 6
6.2 | Deploy dashboard to a cloud platform |  |  | Week 6
6.3 | Create deployment guide and usage instructions |  |  | Week 6
6.4 | Compile final documentation and project summary |  |  | Week 6